## Sheet1
Sprint 1 (3 Members)
|  | Sprint 1 |  | Sprint 2 |  | Sprint 3
Task | Est. Time per Task | Day | Remaining Est Time | Day | Remaining Est Time
Set up Physical board | 30 | 1 | 280 | 1 | 290
Create GIThub repository | 30 | 2 | 220 | 2 | 270
Set up trello | 30 | 3 | 180 | 3 | 240
Select Group Name | 30 | 4 | 160 | 4 | 240
Create whatsapp group | 10 | 5 | 110 | 5 | 240
Set up Burndown data file | 30 | 6 | 50 | 6 | 60
Select Group Logo | 30 | 7 | 10 | 7 | 60
Add group members to whatsapp group | 20
aquire sticky notes | 10
Discuss project plan | 30
Gather data for burndown chart | 30
280
Sprint 2 (4 members) | Est. Time per Task
Modify Logo | 30
Investigate CI in general Eoin | 30
Create Burndown chart for last week | 30
Investigate CI in general Danial | 30
Investigate CI in general Eoghan | 30
Investigate CI in general James | 30
Set up IBM Cloud | 20
Create google doc for project dictionary | 30
Share dictionary | 10
Add to dictionary | 30
Review Sprint 1 | 30
At this scale the management of the agile processes takes as much time as the work itself
Sprint 3 | Est. Time per Task